**TSPi Schedule Planning Template - Form SCHEDULE**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name | | Angela Suarez | | | | | Date | | 13/04/2015 | | |
| Team | | Making Solutions | | | | | Instructor | | Daniel Benavides | | |
| Part/Level | | Integración | | | | | Cycle | | 1 | | |
|  | | | | | | | | | | | |
|  |  | | **Plan** | | | **Actual** | | | | | |
| **Week**  **No.** | **Date** | | **Direct**  **Hours** | **Cumulative**  **Hours** | **Cumulative**  **Planned**  **Value** | **Hours** | | **Cumulative**  **Hours** | | **Week**  **Earned Value** | **Cumulative**  **Earned Value** |
| 1 | 04/03/15 | | 1 | 1 | 4% |  | |  | |  |  |
| 2 | 18/03/15 | | 2 | 3 | 11% |  | |  | |  |  |
| 2 | 20/03/15 | | 2 | 5 | 18% |  | |  | |  |  |
| 2 | 22/03/15 | | 1 | 6 | 21% |  | |  | |  |  |
| 2 | 23/03/15 | | 1 | 7 | 25% | 4.41 | | 4.41 | | 25.92% | 25.92% |
| 3 | 25/03/15 | | 1 | 8 | 29% |  | |  | |  |  |
| 3 | 27/03/15 | | 2 | 10 | 36% |  | |  | |  |  |
| 3 | 29/03/15 | | 2 | 12 | 43% |  | |  | |  |  |
| 3 | 30/03/15 | | 1 | 13 | 46% | 9,5 | | 13,91 | | 22.22% | 48.17% |
| 4 | 01/04/15 | | 1 | 14 | 50% |  | |  | |  |  |
| 4 | 03/04/15 | | 2 | 16 | 57% |  | |  | |  |  |
| 4 | 05/04/15 | | 4 | 20 | 71% |  | |  | |  |  |
| 4 | 06/04/15 | | 1 | 21 | 75% | 20 | | 33,91 | | 28.57% | 76,74% |
| 5 | 08/04/15 | | 1 | 22 | 79% |  | |  | |  |  |
| 5 | 10/04/15 | | 2 | 24 | 86% |  | |  | |  |  |
| 5 | 12/04/15 | | 2 | 26 | 93% |  | |  | |  |  |
| 5 | 13/04/15 | | 1 | 27 | 96% | 5,2 | | 39.11 | | 23,29% | 98% |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |
|  |  | |  |  |  |  | |  | |  |  |